## Sheet1
CAB | Description | Contact | Notes
54153* | Bar code on Austin clinic face sheet | Vaughan, Terri M. <Vaughan.Terri@mayo.edu>
54276 | LC - Medicare Secondary Payor audit | Phillips, Carol <Phillips.Carol1@mayo.edu> | Sent email 7/6 to set up call 7/8 - reached out to Fick, Christine L. <Fick.Christine@mayo.edu> on 7/7 to see if CAB is still needed 8/4 - Followed up again
56091 | OW-MRN# on Diabetic Summary doesn't match | Tiedtke, Steven <Tiedtke.Steven@mayo.edu> | 6/30 - Sent email to set up call 7/6 - Still no response. Followed up to see if CAB was still needed. 7/8 - this report is no longer needed
57788 | Dialysis Schedule Worksheet | Wolf, Renae <Wolf.Renae@mayo.edu> | 7/6 - Sent email to set up call
58205 | Scheduling Overnight Report for AL | Tiedtke, Steven <Tiedtke.Steven@mayo.edu> | 7/6 - Sent email to set up call 7/8 - this report is no longer needed
58625 | Oxygen Orderable (Prescription/Documented Med by Hx) | Hines, Lois C., R.Ph. <Hines.Lois@mayo.edu> | 7/6 - Lois responded with email stating request is now low priority and does not need to be worked on
58709* | Facesheet for XR | Vail, Angela <Vail.Angi@mayo.edu> | 7/6 - Sent email to set up call 7/8 - meeting set up for 7/9 @1230 to review 7/9 - remove barcodes. Use attached link to format the work appropriately so it can be used in the XR application
59431 | SWWI - request to have printer added to 'Warfarin Dietary' report | Kujak, Charlie <kujak.charlie@mayo.edu>
59557 | IV Label code format - move dose / dose unit | Lane, Trudi L., R.Ph. <Lane.Trudi@mayo.edu> | 7/6 - Trudi is following up with the site as to whether the request is still necessary. Sent follow-up email to see if they replied. Got an automated reply stating she is OOO until 7/17. 7/9 - No response from user, so she is closing the CAB.
59643 | Services to exclude from Patient Portal | multiple contacts | Stage after portal code goes into MHPRD. 7/6 - outstanding email to Denise/Mario about whether portal code has been completed or not 7/8 - Denise is waiting for a test patient before she can continue work on her end. Waiting for that to be done before I can continue
60030 | Uninitiated Powerplan Report - Filter by Nursing Unit | Horgen, Billie <Horgen.Billie@mayo.edu>
60033 | Patient Friendly Medication List - Page Break (phase 2)
60111* | add Free Text PCP field to facesheet | Robinson, Jill <Robinson.Jill@mayo.edu> | 7/6 - Sent email to set up call 7/8 - Call set-up Friday @6:30 to discuss
61517 | Adjust barcode placement Adult Armband labels |  | Label Program. Look at when the rest of these are done
61671 | Cerner Barcode Creation |  | Label Program. Look at when the rest of these are done
62025 | Unknown Queue - Report - Add a Column | Sorenson, Cathy <Sorenson.Cathy@mayo.edu>
65324 | Order Sheet printing out with date/time incorrect | Tiedtke, Steven <Tiedtke.Steven@mayo.edu> | 7/8 - Sent email to set up call
65872 | Add ME records to EU Patient Registration Updates - in EMPI reports | Goettl, Tracy <Goettl.Tracy2@mayo.edu>
66411 | Reoccuring Accounts/Accounts with no assigned Date |  | Never received email